## Table 1
Consultant: |  | Name of Responsible Party:
Contact Information
| Action Item | Practice | PPS | Other | Date Completed
Complete 150-180 Days Before Opening:
1 | Select legal counsel to assist with start-up documents |  |  |  | / /
2 | Obtain your professional license |  |  |  | / /
3 | Determine your practice entity type |  |  |  | / /
4 | Choose an appropriate name for the practice / develop logo |  |  |  | / /
5 | Apply for a Federal Identification Number |  |  |  | / /
6 | Obtain Federal and State Narcotic Licenses, as necessary (DEA) |  |  |  | / /
7 | Determine practice location |  |  |  | / /
8 | Obtain a Medicare number and new NPI |  |  |  | / /
9 | Initiate enrollment with insurance plans |  |  |  | / /
10 | Apply for a CLIA Certificate, if applicable |  |  |  | / /
11 | Determine appropriate site and office improvements needed |  |  |  | / /
12 | Develop budget/determine financial resources available, including amount of capital available for Start-Up costs |  |  |  | / /
13 | Determine the office and medical equipment needed |  |  |  | / /
14 | Develop cash flow projections |  |  |  | / /
15 | Prepare a Commercial Loan Proposal (CLP) |  |  |  | / /
16 | Open a checking account |  |  |  | / /
17 | Negotiate and finalize leasehold arrangements for office space |  |  |  | / /
18 | Start on website and marketing campaign |  |  |  | / /
19 | Finalize office layout |  |  |  | / /
20 | Determine deadline for listing your phone number in telephone book and reserve the office phone number |  |  |  | / /
Complete 90-120 Days Before Opening:
21 | Arrange for insurance coverages:
| A. Health |  |  |  | / /
| B. Worker’s Compensation |  |  |  | / /
| C. General Business Liability |  |  |  | / /
| D. Malpractice |  |  |  | / /
22 | Apply for membership in County and State Medical Associations as well as specialty organizations |  |  |  | / /
23 | Apply for State Unemployment and State Income Tax Numbers |  |  |  | / /
24 | Order equipment and furniture |  |  |  | / /
25 | Select, purchase and/or lease appropriate computer system for billing |  |  |  | / /
26 | Decide on type of medical records system, and place order for the same |  |  |  | / /
27 | Acquire a telephone system |  |  |  | / /
28 | Arrange for answering service |  |  |  | / /
29 | Obtain:
| Cellular phone service |  |  |  | / /
| Other communication services |  |  |  | / /
30 | Arrange for laundry, janitorial, and security services |  |  |  | / /
31 | Arrange for transcription service, if appropriate |  |  |  | / /
32 | Arrange for a payroll service, if appropriate |  |  |  | / /
33 | Arrange for Laboratory, X-ray and other support services as needed |  |  |  | / /
34 | Determine office hours and determine appointment scheduling system |  |  |  | / /
35 | Develop an accounts payable system |  |  |  | / /
36 | Determine proper fee schedule |  |  |  | / /
37 | Develop an appropriate marketing strategy |  |  |  | / /
38 | Develop a practice web site |  |  |  | / /
39 | Conduct telephone interviews/evaluations of Practice Manager candidates |  |  |  | / /
Complete 30-90 Days Before Opening
40 | Meet with potential referrral sources |  |  |  | / /
41 | Develop a system for communication of Hospital charges |  |  |  | / /
42 | Compile a list of in-house lab tests, and other ancillary tests to be done
43 | Design Superbill/Encounter Form/Charge Slip (printing additional) |  |  |  | / /
44 | Order clinical and office supplies |  |  |  | / /
45 | List lab supplies needed and place the initial order |  |  |  | / /
46 | Do the same for all other ancillaries, if any
47 | Order stationery, business cards, letterhead, envelopes, etc. |  |  |  | / /
48 | Obtain current CPT and ICD-9 coding books |  |  |  | / /
49 | Develop an Office Policy / Procedures Manual |  |  |  | / /
50 | Develop a Personnel Policy Manual draft with HR Disc |  |  |  | / /
51 | Secure required Federal and State Employment posters |  |  |  | / /
52 | Evaluate the Wage Scale (Regional); set wage parameters for each position in the office |  |  |  | / /
53 | Create employee personnel files |  |  |  | / /
54 | Use HR Help Disc to develop:
| Job Descriptions |  |  |  | / /
| Performance Appraisals |  |  |  | / /
| Personnel Action Forms |  |  |  | / /
| Employee Surveys |  |  |  | / /
| Annual Compensation Summary |  |  |  | / /
55 | Secure OSHA & CLIA Compliance Plans. OSHA Manuals, and Training |  |  |  | / /
56 | Secure HIPAA Manuals and Training |  |  |  | / /
57 | Arrange for employee training on your billing/EMR system |  |  |  | / /
58 | Schedule Front Desk Collection Training to include Insurance Verification Training |  |  |  | / /
59 | Develop a Patient Information Brochure |  |  |  | / /
60 | Choose and Order publications for Reception Room and Physicians |  |  |  | / /
61 | Announce opening of the Practice and plan for an Open House (Cards/newspaper/mailing) |  |  |  | / /
62 | Assemble a patient registration packet |  |  |  | / /
65 | Begin accepting appointments |  |  |  | / /